To print this document the show/hide symbol (¶) must be off – this will enable the document to indicate the correct number of total pages.

NOTE:  This Section 01027 "Applications for Payment” includes procedural requirements for preparation and submittal of Contractor’s Applications for Payment under lump sum contracts. Revise paragraphs carefully to reflect specific project requirements, or delete them if they do not apply.

The header and footer for each page of the Project Manual shall match the format, font (Times New Roman), size (11 pt), font style (BOLD & CAPITALIZED) and line boarders, of the header and footer shown herein.. The header of each page shall contain the Section Number, the Section Title, and the page number & number of pages as shown herein. The footer shall contain the project number in the right hand side as shown herein, including the Table of Contents.  Division 0 and 1 contain a revision date in the left side of the footer This date is to remain as it is for Department informational purposes only and should not be altered by the Architect/Engineer.

DO NOT include Paragraphs or parts of Paragraphs in the project manual, which have no applicability to the specific project.  KEEP IN NUMERICAL SEQUENCE, If A PART IS NOT USED OR ELIMINATED THEN RENUMBER THE FOLLOWING SECTIONS.   IF A PART IS NOT APPLICABLE TO A SPECIFIC PROJECT THEN DESIGNATE IT AS (NOT APPLICABLE).  Also, please review the General Conditions carefully and coordinate the requirements of those Articles including the Definitions.

# PART 1 - GENERAL

## 1.1	RELATED DOCUMENTS

### A.	Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

## 1.2	SUMMARY

NOTE:  Retain paragraph below unless project is constructed under multiple prime contracts.

### A.	This Section specifies procedures for preparation and submittal of the Contractor's Applications for Payment.

### B.	Related Sections:  The following Sections contain requirements that relate to this Section.

NOTE:  Revise subparagraph below if the specification is not in accordance with the General Conditions or Supplementary Conditions.

#### 1.	General Conditions: Articles: 27 “Schedule of Values, Application for Payment”; 28 “Partial Payments”; 31 “Final Payment”; and 32 “Owner’s Right to Withhold Payments”.

#### 2.	Division 1 Section 01035 “Modification Procedures”

#### 3.	Division 1 Section 01300 “Submittals”.

NOTE:  Retain paragraph below that is the type of schedule used for the project..

#### 4.	Division 1 Section 01310 “Construction Schedules”.

OR

#### 4.	Division 1 Section 01315 “CPM Schedules”.

#### 5.	Division 1 Section 01700 “Contract Closeout”: Final Payment.

## 1.3	SCHEDULE OF VALUES

NOTE:  Retain paragraph below unless project is constructed under multiple prime contracts.

### A.	Coordination:  Coordinate preparation of the “Schedule of Values” with preparation of the CPM Schedule or Construction Schedule. Use “Schedule of Values” form as required by the Owner

NOTE:  Revise the time period in paragraph below if necessary to suit project requirements.

#### 1.	Submit the “Schedule of Values” to the Construction Administrator at the earliest possible date but no later than (21) twenty-one Calendar Days after Contract Start Date.

NOTE:  Delete the requirement below if phasing is not required.  For large projects, consider revising the requirement to provide sub-schedules for separate floors or large individual areas.

#### 2.	Sub-schedules:  Where Work is separated into phases requiring separately phased payments, provide sub-schedules showing values correlated with each phase of payment.

NOTE:  Retain the requirements below.  Revise to suit project requirements.  If desired, include a sample schedule of values at end of section.  Delete electronic media requirement if specific project is small.

### B.	Format and Content:  Use the Project Manual Table of contents as a guide to establish the format for the “Schedule of Values”.   Provide at least one line item for each the Specification Section on electronic media printout.

#### 1.	Identification: Project identification on the Schedule of Values shall include, but not be limited to, the following:

NOTE:  Modify the list below to suit project requirements by adding or deleting items.

##### a.	Owner

##### b.	Project Number

##### c.	Project Name

##### d.	Project Location

##### e.	Contractor's name and address.

#### 2.	Arrange the “Schedule of Values” in tabular format as required by the Owner, containing separate columns including, but not limited to, the following Items:

NOTE:  Modify the list below to suit project requirements by adding or deleting items

##### a.	Item Number.

##### b.	Description of Work with Related Specification Section or Division Number.

##### c.	Scheduled Values broken down by description number, type material, units of each material.

##### d.	Name of subcontractor.

##### e.	Name of manufacturer or fabricator.

##### f.	Name of supplier.

##### g.	Retainage.

##### h.	Contract sum in sufficient detail.

#### 3.	Percentage of Contract Sum to nearest one-hundredth percent, adjusted to total 100 percent.

#### 4.	Provide a breakdown of the Contract Sum in sufficient detail to facilitate continued evaluation of Applications for Payment and progress reports.  Coordinate with the Project Manual table of contents.  Break principal subcontract amounts down into several line items.

#### 5.	Round amounts to nearest whole dollar; the total shall equal the Contract Sum.

NOTE:  Retain the requirement below.  Strengthen to protect against undue front-end loading, if necessary. Delete the requirement below if specifications do not include unit-cost allowances.

#### 6.	Unit-Cost Allowances:  Show the line-item value of unit-cost allowances, as a product of the unit cost, multiplied by the measured quantity.  Estimate quantities from the best indication in the Contract Documents.

NOTE:  Retain the requirement below.  Modify as required to suit project requirements.

#### 7.	General Conditions:  Show line items for indirect costs and margins on actual costs only when such items are listed individually in Applications for Payment.  Each item in the Schedule of Values and Applications for Payment shall be complete.  Include the total cost and proportionate share of general overhead and profit margin for each item.

##### a.	Temporary facilities and other major cost items that are not direct cost of actual work-in-place may be shown either as separate line items in the Schedule of Values or distributed as general overhead expense, at the Contractor's option.

## 1.4	APPLICATIONS FOR PAYMENT

NOTE:  Revise the requirement below as necessary.

A.	Each Application for Payment shall be consistent with previous applications and payments as certified by the Architect and Construction Administrator and paid for by the Owner.

#### 1.	The initial “Application for Payment”, the “Application for Payment”, at time of “Substantial Completion”, and the final “Application for Payment”, involve additional requirements.

### B.	Payment-Application Terms:  The Owner will process monthly progress payments.  The Contractor may submit applications for payment on a monthly basis.

### C.	Payment-Application Forms:  Use the “Application for Payment” form as required by the Owner.  Present the required information on electronic media printout or Owner approved form, multiple pages should be used if required.

#### 1.	For each item, provide a column including but not limited to the following items:

##### Item Number.

##### Description of Work and Related Specification Section or Division.

##### Scheduled Value, break down by units of material and units of labor.

##### Work Completed from previous application.

##### Work Completed this period.

##### Materials presently stored.

##### Total Completed and stored to date of application.

##### Percentage of Completion.

##### Balance to Finish.

##### Retainage

#### D.	Application Preparation: Complete every entry on the Application form. At the time of  Final Payment only, include an executed Application form by a person authorized to sign legal documents on behalf of the Contractor.  The Construction Administrator will return incomplete Applications without action.

### 1.	Entries shall match data on the “Schedule of Values”.

#### 2.	Include amounts of Change Orders issued prior to the last day of the construction period covered by the application.

NOTE:  Revise the number of copies below to suit specific project or DPW requirements.(standard is indicated) increase to 9 copies of required for CA services.

#### Transmittal: Except for final payment, submit to the Construction Administrator by a method ensuring receipt within forty-eight (48) hours.  One (1) complete, signed and notarized original of each Application for Payment, including lien waivers and similar attachments when required, along with six (6) copies. For Final Payment, nine (9) complete, signed and notarized copies shall be submitted.

#### 1.	Transmit each copy with a transmittal form listing attachments and recording appropriate information related to the application, in a manner acceptable to the Architect.

NOTE:  Insert instructions for preparation and submittal of waivers or releases here if not stated in supplementary conditions.

### Applications for Payment:  Administrative actions and submittals, that must precede or coincide with submittal of the first Application for Payment and all subsequent Application for Payments including, but not limited to, the following items:

NOTE:  Revise the list below to suit project requirements.

#### List of subcontractors and suppliers’ name, FEIN/Social Security numbers, and Connecticut Tax Registration Numbers.

#### List of principal suppliers and fabricators.

#### Schedule of Values.

#### Contractor's Construction Schedule (preliminary if not final).

#### Schedule of principal products.

#### Submittal Schedule (preliminary if not final).

#### List of Contractor's staff assignments.

#### List of Contractor's principal consultants.

#### Copies of all applicable permits.

#### Copies of authorizations and licenses from governing authorities for performance of the Work.

#### Proof that as-built documents are updated as required by Section 01700 “Contract Closeout”.

NOTE:  Delete items submitted before executing the contract from those listed below.

#### 12.	Initial as-built survey and damage report, if required.

### G.	Application for Payment at Substantial Completion:  Following issuance of the Certificate of Substantial Completion submit an Application for Payment form, use the form as required by the Owner.  Present the required information on electronic media printout.

#### 1.	This application shall reflect Certificates of Partial Substantial Completion issued previously for Owner occupancy of designated portions of the Work..

#### 2.	Administrative actions and submittals that shall precede or coincide with this application include, but are not limited to, the following:

NOTE:  Delete from and add to the following list to suit project requirements.

##### Occupancy permits and similar approvals.

##### Warranties (guarantees) and maintenance agreements.

##### Test/adjust/balance records.

##### Maintenance instructions.

##### Meter readings.

##### Startup performance reports.

##### Changeover information related to Owner's occupancy, use, operation, and maintenance.

##### Final cleaning.

##### Application for reduction of retainage and consent of surety.

##### Advice on shifting insurance coverage.

##### Final progress photographs.

##### List of incomplete Work, recognized as exceptions to Architect's Certificate of Substantial Completion.

### H.	Final Payment Application:  Administrative actions and submittals that must precede or coincide with submittal of the final Application for Payment include, but are not limited, to the following:

NOTE:  Delete from and add to the list below to suit project requirements.  Check with Project Manager about the need for additional affidavits and other requirements.  See requirements for Final Acceptance, Final Completion, Final Inspection, and Final Payment, in the General Conditions and Supplementary Conditions.

#### Completion of Project Closeout requirements.

#### Completion of list of items remaining to be completed as indicated on the attachment to the Certificate of Substantial Completion.

#### Ensure that unsettled claims will be settled.

#### Ensure that incomplete Work is not accepted and will be completed without undue delay.

#### Transmittal of required Project construction records to the Owner (including as-built documents Reference Section 01700 “Contract Closeout”).

#### Certified property survey.

#### Proof that taxes, fees, and similar obligations were paid.

#### Removal of temporary facilities and services.

#### Removal of surplus materials, rubbish, and similar elements.(Reference Section 01590 “Construction waste Management”)

#### Change of door locks to Owner's access.

#### The requirements of the General Conditions and Supplementary Conditions for Final Acceptance, Final Completion, Final Inspection, and Final Payment.

#### Asbestos, Lead or other hazardous material manifests.

#### Completion of “Building Contractor Reporting Form” as supplied by Department of Public Works, for all Contractors, Subcontractors, Vendors, Suppliers, etc. who work on the Contract.  The form includes the following information:

##### Contractor/Subcontractor name.

##### FEIN/Social Security Numbers

##### Connecticut Tax Registration Numbers

##### Type of work

##### Name of business and address

##### Remittance address.

# PART 2 - PRODUCTS (Not Applicable)

# PART 3 - EXECUTION (Not Applicable)

END OF SECTION 01027