To print this document the show/hide symbol (¶) must be off – this will enable the document to indicate the correct number of total pages.

NOTE:  This Section 01040 "Coordination” includes requirements for general project coordination procedures, conservation, coordination of drawings, administrative and supervisory personnel, and cleaning and protection.

Revise paragraphs carefully to reflect specific project requirements, or delete them if they do not apply.

The header and footer for each page of the Project Manual shall match the format, font (Times New Roman), size (11 pt), font style (BOLD & CAPITALIZED) and line boarders, of the header and footer shown herein.. The header of each page shall contain the Section Number, the Section Title, and the page number & number of pages as shown herein. The footer shall contain the project number in the right hand side as shown herein, including the Table of Contents.  Division 0 and 1 contain a revision date in the left side of the footer This date is to remain as it is for Department informational purposes only and should not be altered by the Architect/Engineer.

DO NOT include Paragraphs or parts of Paragraphs in the project manual, which have no applicability to the specific project.  KEEP IN NUMERICAL SEQUENCE, If A PART IS NOT USED OR ELIMINATED THEN RENUMBER THE FOLLOWING SECTIONS.  IF A PART IS NOT APPLICABLE TO A SPECIFIC PROJECT THEN DESIGNATE IT AS (NOT APPLICABLE).  Also, please review the General Conditions carefully and coordinate the requirements of those Articles including the Definitions.

# PART 1 - GENERAL

## 1.1	RELATED DOCUMENTS

### A.	Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

## 1.2	SUMMARY

### A.	This Section includes administrative and supervisory requirements necessary for coordinating construction operations including, but not necessarily limited to, the following:

NOTE:  Delete requirements not included from the list below.  Insert special requirements, as necessary.

#### 1.	General project coordination procedures.

#### 2.	Conservation.

#### 3.	Coordination Drawings, including Site Logistics Plans.

#### 4.	Administrative and supervisory personnel.

#### 5.	Cleaning and protection.

### B.	Related Sections:  The following Sections contain requirements that relate to this Section:

NOTE:  Delete the 2 subparagraphs below if this section includes field engineering or project meetings.  This section often includes these subjects on small projects.

#### 1.	Division 1 Section 01050 "Field Engineering" specifies procedures for field engineering services, including establishment of benchmarks and control points.

#### 2.	Division 1 Section 01200 "Project Meetings" for progress meetings, coordination meetings, and pre-installation conferences.

NOTE:  Retain paragraph below that is the type of schedule used for the project.  Delete Schedule type not applicable.

#### 3.	Division 1 Section 01310 “Construction Schedules”.

OR

#### 3.	Division 1 Section 01315 “CPM Schedules”.

#### Division 1 Section 01500 “Construction Facilities and Temporary Controls.”

#### Division 1 Section 01600 "Materials and Equipment" for coordinating general installation.

#### Division 1 Section 01700 "Contract Closeout" for coordinating contract closeout.

#### Division 1 Section 01810 “Commissioning”.

#### Division 17 Section 17100 “Commissioning Requirements”, defines the commissioning process.

## 1.3	CONSTRUCTION ADMINISTRATOR

A.	Construction Administrator:

#### 1.	The Construction Administrator is identified in Division 1 Section 01010 “Summary of Work”.

#### 2.	Construction Mobilization:

##### a.	Cooperate with the Construction Administrator in the allocation of mobilization areas of the site, for field offices and sheds, for agency facility access, traffic, and parking facilities.

##### b.	During Construction, coordinate use of site and facilities through the Construction Administrator.

##### c.	Comply with Construction Administrators procedures for intra-project communications; submittals, reports and records, schedules, coordination drawings, and recommendations; and resolution of ambiguities and conflicts.

NOTE:  Responsibility for providing temporary utilities and construction facilities is identified in Section 01010 Summary of Work.  Delete or revise and edit paragraphs below as required for specific project.

##### d.	Comply with instructions of the Construction Administrator for use of temporary utilities and construction facilities.

##### e.	Coordinate field engineering layout as specified in Division 1 Section 01050 “Field Engineering” for work under the instructions of the Construction Administrator.

## 1.4	COORDINATION

### A.	Coordinate construction operations included in various Sections of these Specifications to assure efficient and orderly installation of each part of the Work.  Coordinate construction operations included under different Sections that depend on each other for proper installation, connection, and operation.

#### 1.	Schedule construction operations in the sequence required to obtain the best results where installation of one part of the Work depends on installation of other components, before or after its own installation.

#### 2.	Coordinate installation of different components to assure maximum accessibility for required maintenance, service, and repair.

#### 3.	Make provisions to accommodate items scheduled for later installation.

### B.	Where necessary, prepare memoranda for distribution to each party involved, outlining special procedures required for coordination.  Include such items as required notices, reports, and attendance at meetings.

#### 1.	Prepare similar memoranda for the Construction Administrator, Owner and separate contractors where coordination of their work is required.

### C.	Administrative Procedures: Coordinate scheduling and timing of required administrative procedures with other construction activities to avoid conflicts and assure orderly progress of the Work.  Such administrative activities include, but are not limited to, the following:

NOTE:  Insert other administrative activities needed to suit project requirements.

#### 1.	Preparation of schedules.

#### 2.	Installation and removal of temporary facilities.

#### 3.	Delivery and processing of submittals.

#### 4.	Progress meetings.

#### 5.	Project closeout activities.

## SUBMITTALS

### A.	Coordination Drawings:  Prepare coordination drawings to complete detailed coordination of systems and components and to integrate information about fabrication and installation.

#### Thoroughly prepare coordination drawings, as further stipulated in Part 3, “Execution”, reviewing all contract documents and consulting with all entities contributing to or involved with each portion of the work under consideration.

##### Show the relationship of all components shown on any separate Shop Drawings.

##### Indicate required desired installation sequences.

##### Comply with requirements contained in Division 1 Section 01300 “Submittals”.

#### Prepare coordination drawings for installation of all products and materials fabricated by separate entities.

NOTE: Edit paragraph examples for the project.

#### Prepare coordination drawings where limited space availability necessitates maximum utilization of space for efficient installation of different components, including but not limited to: all site-utility entry points; all ceiling and roof cavities in all areas; all electrical, telecommunications and mechanical rooms; all stage-boundary interface areas; all laboratories, animal-handling rooms and data rooms; all classrooms and seminar rooms; all lecture halls and their support spaces; all video studios, broadcast classrooms and their support facilities; and all such other conditions required to coordinate the work.

#### Prepare a Site Logistics Plan(s) showing:  The entire project area and limits; all routes into and out of site; all staging and stockpiling and lay-down areas; all aspects of phasing/staging; all parking, paving and fencing; and all specific provisions to satisfy requirements of Division 1 Sections, including but not limited to Field Engineering and Construction Facilities and Temporary Controls.  The Site Logistics Plan shall coincide with and complement the general staging plans and site plans outlined in the contract bidding documents.  It is intended that the General Contractor shall present this refined plan for approval by the Construction Administrator.  The fencing shown on this plan is required for all phases.  Exact placement and timing of installations and removals will be reviewed and approved by the Construction Administrator prior to implementation.  Specified in Division 2 is an additional allotment of various fencing, which the Contractor shall provide, install, and relocate at various intervals, for installation and removal by the General Contractor per the direction of the project’s Construction Administrator.  This staging and logistics plan will require refinement and change for each phase/stage of the project.  The Site logistics Plan(s) shall be drawn at a scale no smaller than 1”=40’ and shall be submitted as stipulated in Division 1 Section “Applications for Payment”, but in now case later than (30) days after Notice to Proceed.

#### Prepare coordination drawings showing locations of surface recesses and voids, as well as offsets and breaks, requiring filling and/or feathering, both those initially visible and those discovered during the course of work.  Review with Owner and Architect to obtain direction for filling and feathering.  Revise drawing(s) to record directions for same for field and record purposes.

### B.	Staff Names:  Prior to the contract start date, submit a list of the Contractor's principal staff assignments, including the superintendent, project safety officer, and other personnel in attendance at the Project Site.  Identify individuals and their duties and responsibilities.  List their addresses and telephone numbers.

#### Post copies of the list in the Project meeting room, the temporary field office, and each temporary telephone.

#### Provide resumes of each staff member proposed for the project.  This shall include the Project Manager, Project Superintendent and Safety Officer.

NOTE:  Insert special requirements for the superintendent and assistants that exceed requirements contained in General and Supplementary Conditions.

# PART 2 - PRODUCTS (Not Applicable)

# PART 3 - EXECUTION

## 3.1	GENERAL COORDINATION PROVISIONS

### A.	Inspection of Conditions:  Require the Installer of each major component to inspect both the substrate and conditions under which Work is to be performed and coordinate such inspections with the Construction Administrator and authorities having jurisdictions.  If unsatisfactory conditions exist notify the Construction Administrator immediately.  Do not proceed until unsatisfactory conditions have been corrected in an acceptable manner.

### The Contractor shall coordinate temporary enclosures with required inspections and tests to minimize the necessity of uncovering completed construction for that purpose.

### Coordination Drawings: Before construction work can begin, the Contractor shall submit to the Architect coordination drawings in the form of (a) reproducible (vellum) transparencies at not less than 1/4-inch scale and (b) CAD files of the coordination drawings on CDROM.  Such drawings will be required throughout all areas for trades as described below.  These drawings shall show resolutions of trade conflicts in congested areas.  The Architect will supply base drawings(with the title blocks removed), including floor plans, reflected ceiling plans, and structural framing plans, in the form of electronic CAD files on CDROM, using the AutoCAD release edition specified with the files, to the General Contractor for distribution to the trades for use in developing the coordination drawings.  Each trade contractor shall create separate layers within the CAD files to show the work of their trade.  Prepare coordination drawings as follows:

#### The HVAC subcontractor shall initiate 1/4-inch scale drawings done on AutoCAD (latest version) showing ducts and piping in plan and section.  Sheet metal shop drawings must be approved prior to starting coordination drawings.

#### The Sprinkler subcontractor shall then add layers to superimpose his piping layout on the coordination drawings.

#### The Electrical subcontractor shall then add layers to superimpose all the electrical information on the coordination drawings.  Said information is to include but not necessarily be limited to cable trays, equipment, lighting, conduits, bus duct, etc.  Show space allowances reserved for work under other contracts, such as audio-visual wiring and equipment.

#### The Plumber subcontractor shall then add layers to complete the coordination drawing by drawing his piping (including pitch) on the coordination drawings.

#### Contractors for specialties, furnishings, equipment and special construction shall add layers to show their work to assure full coordination of all systems.

#### The Construction Administrator shall review the completed coordination drawings for general compliance and then submit them to the Architect for his review.  All subcontractors shall rework the drawings until all systems are properly coordinated.

#### The Ceiling subcontractor shall utilize the drawings to prepare acoustic panel ceiling drawings and any other suspended ceiling drawings, and shall indicate areas of conflict with the work of other trades by drafting the location of grids, panels and tiles.

#### The General Construction Contractor shall indicate Architectural/Structural conflicts or obstacles and coordinate to suit the overall construction schedule.  The Contractor shall locate all precut and prefabricated holes and openings in structural steel on the CAD coordination drawing files as required for HVAC, plumbing, fire protection and electrical work.  The Contractor shall coordinate these holes and openings with the structural steel fabricator during the structural steel shop drawing development phase.  Coordination to take place on schedule so as to permit shop fabrication of all structural steel holes and openings.  The Owner will not be held responsible for the costs associated with field fabrication of structural openings resulting from the lack of timely and thorough coordination.

#### The General Construction Contractor shall expedite all drawing work and coordinate to suit the construction schedule.  The General Construction Contractor shall then review these drawings and compare them with the Architectural, Structural, Equipment, and other drawings and determine that all of the work can be installed without undue interference.  Prior to the submittal to the Architect, areas of potential conflict shall be brought to the attention of the General Contractor who shall convene a coordination meeting of all parties involved, for the purpose of resolving all utility conflicts.  The General Contractor shall supervise and direct corrective measures and have all trades sign acceptance of the drawings.  Submit (4) four hard copies of each drawing to the Architect and (2) copies to the Construction Administrator for the record, and only after all conflicts have been accommodated.

#### If the coordination meeting fails to resolve coordination conflicts, the General Contractor shall indicate the nature of such conflicts in a detailed RFI, proposing the most economical solution.

#### Trades work in a given bay or area should not proceed until all trades foreman agree on the exact arrangements for each room or area.  If a given trade proceeds prior to trades approval, then if necessary, that trade shall revise their work, if necessary, at no extra cost, in order to permit others to proceed.

#### Submit all coordination drawings on CD-ROM, in addition to hard copy.

### D.	The Construction Administrator will meet with the Contractor on all major items of coordination.

## 3.2	CLEANING AND PROTECTION

NOTE:  Provisions in the next article reduce or eliminate the need for similar provisions in other sections.  Insert provisions needed because of unusual project conditions.  Specify unusual provisions for specific work in the individual unit of work section.

### A.	Clean and protect construction in progress and adjoining materials in place, during handling and installation.  Apply protective covering, where required, to assure protection from damage or deterioration.

### B.	Clean and provide maintenance on completed construction as construction per manufacturers requirements through the remainder of the construction period.  Adjust and lubricate operable components to assure operability without damaging effects.

### C.	Limiting Exposures:  Supervise construction operations to assure that no part of the construction, completed or in progress, is subject to harmful, dangerous, damaging, or otherwise deleterious exposure during the construction period.  Where applicable, such exposures include, but are not limited to, the following:

NOTE:  Delete items from the list below that are not appropriate for the project.  Add items to suit project requirements.

#### 1.	Excessive static or dynamic loading.

#### 2.	Excessive internal or external pressures.

#### 3.	Excessively high or low temperatures.

#### 4.	Thermal shock.

#### 5.	Excessively high or low humidity.

#### 6.	Air contamination or pollution.

#### 7.	Water or ice.

#### 8.	Solvents.

#### 9.	Chemicals.

#### 10.	Light.

#### 11.	Radiation.

#### 12.	Puncture.

#### 13.	Abrasion.

#### 14.	Heavy traffic.

#### 15.	Soiling, staining, and corrosion.

#### 16.	Bacteria.

#### 17.	Rodent and insect infestation.

#### 18.	Combustion.

#### 19.	Electrical current.

#### 20.	High-speed operation.

#### 21.	Improper lubrication.

#### 22.	Unusual wear or other misuse.

#### 23.	Contact between incompatible materials.

#### 24.	Destructive testing.

#### 25.	Misalignment.

#### 26.	Excessive weathering.

#### 27.	Unprotected storage.

#### 28.	Improper shipping or handling.

#### 29.	Theft.

#### 30.	Vandalism.

END OF SECTION 01040