To print this document the show/hide symbol (¶) must be off – this will enable the document to indicate the correct number of total pages.

NOTE:  This Section 01300 "Submittals” includes administrative and procedural requirements for submittals required for performance of the Work.  Submittals include the examples of the following types, contractor's construction schedule, submittal schedule, daily construction reports, shop drawings, product data, samples, quality assurance submittals, and proposed "equals" or "substitutions".  Revise paragraphs carefully to reflect specific project requirements, or delete them if they do not apply.

The header and footer for each page of the Project Manual shall match the format, font (Times New Roman), size (11 pt), font style (BOLD & CAPITALIZED) and line boarders, of the header and footer shown herein.. The header of each page shall contain the Section Number, the Section Title, and the page number & number of pages as shown herein. The footer shall contain the project number in the right hand side as shown herein, including the Table of Contents.  Division 0 and 1 contain a revision date in the left side of the footer This date is to remain as it is for Department informational purposes only and should not be altered by the Architect/Engineer.

DO NOT include Paragraphs or parts of Paragraphs in the project manual, which have no applicability to the specific project.  KEEP IN NUMERICAL SEQUENCE, If A PART IS NOT USED OR ELIMINATED THEN RENUMBER THE FOLLOWING SECTIONS.  IF A PART IS NOT APPLICABLE TO A SPECIFIC PROJECT THEN DESIGNATE IT AS (NOT APPLICABLE).  Also, please review the General Conditions carefully and coordinate the requirements of those Articles including the Definitions.

# PART 1 - GENERAL

## 1.1	RELATED DOCUMENTS

### A.	Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

## 1.2	SUMMARY

### This Section includes administrative and procedural requirements for submittals required for performance of the Work, including but not limited to the following:

NOTE:  Delete items from the example list below that are not appropriate for the project.  Add items to suit project requirements.

#### Submittal schedule.

#### Shop Drawings.

#### Product Data.

#### Samples.

#### Quality assurance submittals.

#### Proposed "Substitutions/Equals".

#### Warrantee samples.

#### Coordination Drawings.

#### O & M Manuals

### Administrative Submittals: Refer to other Division 1 Sections and other Contract Documents for requirements for administrative submittals.  Such submittals include, but are not limited to, the following:

NOTE:  Delete items from the example list below that are not appropriate for the project.  Add items to suit project requirements.

#### Permits.

#### Applications for Payment.

#### Performance and payment bonds.

#### Contractor’s construction schedule.

#### Daily construction reports.

#### Construction Photographs.

#### Insurance certificates.

#### List of subcontractors.

#### Subcontractors/Suppliers FEIN #’s and Connecticut tax registration #.

### Related Sections:  The following Sections contain requirements that relate to this Section:

NOTE:  Delete Division Sections from the list below that are not appropriate for the project.  Add Division Sections to suit project requirements.

#### Division 1 Section 01027 "Application for Payment" specifies requirements for submittal of the Schedule of Values.

#### Division 1 Section 01040 "Coordination" specifies requirements governing preparation and submittal of required Coordination Drawings.

#### Division 1 Section 01200 "Project Meetings" specifies requirements for submittal and distribution of meeting and conference minutes.

NOTE:  Retain paragraph below that is the type of schedule used for the project.  Delete the schedule that is not applicable..

#### Division 1 Section 01310 “Construction Schedules”.

OR

#### Division 1 Section 01315 "CPM Schedule" specifies requirements for contractor's schedule submittal.

#### Division 1 Section 01380 "Construction Photographs" specifies requirements for submittal of periodic construction photographs.

#### Division 1 Section 01400 "Quality Control" specifies requirements for submittal of inspection and test reports.

#### Division 1 Section 01631 "Equals and Substitutions" specifies requirements for submittal of requests to use products other than those specified.

#### Division 1 Section 01700 "Contract Closeout" specifies requirements for submittal of Project Record Documents and warranties at project closeout.

#### Division 1 Section  01740 “Warranties and Bonds”.

## 1.3	DEFINITIONS

### Coordination Drawings show the relationship and integration of different construction elements that require careful coordination during fabrication or installation to fit in the space provided or to function as intended and as identified in the Specification Division 2 through 16.

#### 1.	Preparation of Coordination Drawings is specified in Division 1 Section "Coordination" and may include components previously shown in detail on Shop Drawings or Product Data.

### Field samples are full-size physical examples erected on-site to illustrate finishes, coatings, or finish materials.  Field samples are used to establish the standard by which the Work will be judged.

### Mockups are full-size assemblies for review of construction, coordination, testing, or operation; they are not Samples.

## 1.4	SUBMITTAL PROCEDURES

### Coordination:  Coordinate preparation and processing of submittals with performance of construction activities.  Transmit each submittal sufficiently in advance of performance of related construction activities to avoid delay.

#### Coordinate each submittal with fabrication, purchasing, testing, delivery, other submittals, and related activities that require sequential activity.

#### Coordinate transmittal of different types of submittals for related elements of the Work so processing will not be delayed by the need to review submittals concurrently for coordination.

##### The Architect reserves the right to withhold action on a submittal requiring coordination with other submittals until all related submittals are received.

##### The Architect reserves the right to reject incomplete submitted packages.

#### Processing:  To avoid the need to delay installation as a result of the time required to process submittals, allow sufficient time for submittal review, including time for resubmittals.

NOTE:  Revise the time  periods of subparagraphs below to suit project requirements.

##### Allow (2) two weeks for initial review.  Allow additional time if the Architect must delay processing to permit coordination with subsequent submittals.

##### If an intermediate submittal is necessary, process the same as the initial submittal.

##### Allow (2) two weeks for reprocessing each submittal.

##### No extension of Contract Time will be authorized because of failure to transmit submittals to the Architect sufficiently in advance of the Work to permit processing.

NOTE:  Revise the submittal formats of subparagraphs below to suit project requirements.

### Submittal Preparation:  Place a permanent label, title block or 8-1/2 inches x 11 inches cover page approved by the Architect, on each submittal for identification.  Indicate the name of the entity that prepared each submittal on the label or title block.

#### The minimum number of copies required for each submittal shall be at a minimum 7 copies or as determine otherwise at the pre-construction conference or by the Construction Administrator.

#### Provide a space approximately 4 inches by 5 inches on the label, beside the title block or on the cover page on Shop Drawings to record the Contractor's review and approval markings and the action taken.

#### Include the following information on the label for processing and recording action taken.

NOTE:  Delete items from the example list below that are not appropriate for the project.  Add items to suit project requirements.

##### Project Name and State of Connecticut Project Number.

##### Date.

##### Name and address of the Architect, Construction Administrator, and Owner Representative.

##### Name and address of the Contractor.

##### Name and address of the subcontractor.

##### Name and address of the supplier.

##### Name of the manufacturer.

##### Number and title of appropriate Specification Section.

##### Drawing number and detail references, as appropriate.

##### Indicate either initial or resubmittal.

##### Indicate deviations from Contract Documents.

##### Indicate if "equal" or "substitution".

NOTE:  Revise the submittal process with copy of the transmittal to Construction Administrator and original to Architect as required.

### Submittal Transmittal:  Package each submittal appropriately for transmittal and handling.  Transmit each submittal from the Contractor to the Architect using a transmittal form.  Copy the Construction Administrator on the transmittal.  The Architect will return all submittals to the Contractor after action is taken with a complete copy of the submittal package and one complete copy of the submittal package.  The Architect will not accept submittals received from sources other than the Contractor.

#### 1.	On the transmittal, record relevant information and requests for data.  On the form, or separate sheet, record deviations from Contract Document requirements, including variations and limitations.  Include Contractor's certification that information complies with Contract Document requirements.

## 1.6	SUBMITTAL SCHEDULE

NOTE:  Revise the time periods of subparagraph below to suit project requirements.

### After development and review by the Owner and Architect acceptance of the Contractor's Construction or CPM schedule prepare a complete schedule of submittals.  Submit the schedule to the Construction Administrator within 30 days of Contract Award.

#### Coordinate Submittal Schedule with the list of subcontracts, Schedule of Values, and the list of products as well as the contractor’s Construction or CPM Schedule.

#### Prepare the schedule in chronological order.  Provide the following information:

##### Schedule date for the initial submittal.

##### Related section number.

##### Submittal category (Shop Drawings, Product Data, or Samples).

##### Name of Subcontractor.

##### Description of the part of Work covered.

##### Scheduled date for resubmittal.

##### Scheduled date for the Architect’s final release of approval.

### Distribution:  Following response to the initial submittal, print and distribute copies to the Construction Administrator, Architect, Owner, subcontractors, and other parties required to comply with submittal dates indicated.  Post copies in the Project meeting room and field office.

#### 1.	When revisions are made, distribute to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in construction activities.

### Schedule Updating:  Revise the schedule after each meeting or activity where revisions have been recognized or made.  Issue the updated schedule concurrently with the report of each meeting.

## 1.7	DAILY CONSTRUCTION REPORTS

### A.	Prepare a daily construction report recording the following information concerning events at the site, and submit duplicate copies to the Construction Administrator at weekly intervals:

NOTE:  Delete items from the example list below that are not appropriate for the project.  Add items to suit project requirements.

#### List of subcontractors at the site.

#### Approximate count of personnel at the site.

#### High and low temperatures, general weather conditions.

#### Accidents and unusual events.

#### Meetings and significant decisions.

#### Stoppages, delays, shortages, and losses.

#### Meter readings and similar recordings.

#### List of equipment on site and identify if idle or in use.

#### Orders and requests of governing authorities.

#### Change Orders received, start and end dates.

#### Services connected, disconnected.

#### Equipment or system tests and startups.

#### Partial Completion’s, occupancies.

#### Substantial Completion’s authorized.

#### Equals or Substitutions approved or rejected.

## 1.8	SHOP DRAWINGS

NOTE:  Revise the submittal formats of subparagraphs below to suit project requirements.

### Submit newly prepared information drawn accurately to scale.  Highlight, encircle, or otherwise indicate deviations from the Contract Documents.  Do not reproduce Contract Documents or copy standard information as the basis of Shop Drawings.  Standard information prepared without specific reference to the Project is not a Shop Drawing.

### Shop Drawings include fabrication and installation Drawings, setting diagrams, schedules, patterns, templates and similar Drawings.  Include the following information:

#### Dimensions.

#### Identification of products and materials included by sheet and detail number.

#### Compliance with specified standards.

#### Notation of coordination requirements.

#### Notation of dimensions established by field measurement.

#### Sheet Size:  Except for templates, patterns and similar full-size Drawings, submit Shop Drawings on sheets at least 8-1/2 by 11 inches but no larger than 36 by 48 inches.

#### Submit one (1) reproducible media and seven (7) prints as directed by the Construction Administrator.  The Contractor's submittal shall identify the specification section and/or drawing number applicable to the submittal.

#### Details shall be large scale and/or full size.

### The Contractor shall review the Shop Drawings, stamp with this approval, and submit them with reasonable promptness and in orderly sequence so as to cause no delay in his Workor in the Workof any subcontractor.  Shop Drawings shall be properly identified as specified for item, material, workmanship, and project number.  At the submission, the Contractor shall inform the Architect, in writing of any deviation in the shop drawings from the requirements of the Contract Documents.

### The Architect will review and comment on shop drawings with reasonable promptness so as to cause no delay, but only for conformance with the design concept of the project and with the information given in the Contract Documents.  Refer to Article 5 of General Conditions.  Shop Drawings received by the Architect that indicate insufficient study of drawings and specifications, illegible portions or gross errors, will be rejected outright.  Such rejections shall not constitute an acceptable reason for granting the Contractor additional time to perform the work.

### The Contractor shall make any corrections required by the Architect and shall resubmit the required number of corrected copies of shop drawings until fully reviewed.

### Upon final review submit four (4) additional prints, same as submitted, to the Construction Administrator for his use.

### The Architect's review and comments on shop drawings shall not relieve the Contractor of responsibility for any deviation from the requirements of the Contract Documents.

### Only final reviewed shop drawings are to be used on the project site.

### The Work installed shall be reviewed in accordance with the shop drawings and the drawings and specifications.  Final Review of the shop drawings by the Architect shall constitute acceptance by the State and the Architect of a variation or departure that is clearly identified.  Final reviewed shop drawings shall not replace or be used as a vehicle to issue or incorporate change orders.

## 1.9	PRODUCT DATA

### A.	Collect Product Data into a single submittal for each element of construction or system.  Product Data includes printed information, schedules, such as manufacturer's installation instructions, catalog cuts, standard color charts, roughing-in diagrams and templates, standard wiring diagrams, and performance curves.

#### Mark each copy to show applicable choices and options.  Where printed Product Data includes information on several products that are not required, mark copies to indicate the applicable information.  Include the following information:

Revise the submittal formats of subparagraphs below to suit project requirements.

##### Manufacturer's printed recommendations.

##### Compliance with trade association standards.

##### Compliance with recognized testing agency standards.

##### Application of testing agency labels and seals.

##### Notation of dimensions verified by field measurement.

##### Notation of coordination requirements.

#### Do not submit Product Data until compliance with requirements of the Contract Documents has been confirmed.

#### Preliminary Submittal:  Submit a preliminary single copy of Product Data where selection of options is required.

#### Submittals:  Submit 7 copies of each required submittal; submit 5 copies where required for maintenance manuals.  The Architect will retain one and will return the other marked with action taken and corrections or modifications required.

##### a.	Unless noncompliance with Contract Document provisions is observed, the submittal may serve as the final submittal.

#### Distribution:  Furnish copies of final submittal to installers, subcontractors, suppliers, manufacturers, fabricators, and others required for performance of construction activities.  Show distribution on transmittal forms.

##### Do not proceed with installation until a copy of Product Data is in the Installer's possession.

##### Do not permit use of unmarked copies of Product Data in connection with construction.

NOTE:  Projects requiring sample full-scale mock-ups, the Architect shall identify below and with technical specifications.

## 1.10	SAMPLES

### Submit full-size, fully fabricated Samples cured and finished as specified and physically identical with the material or product proposed.  Samples include partial sections of manufactured or fabricated components, cuts or containers of materials, color range sets, and swatches showing color, texture, and pattern.

#### Store, mount or display Samples on site in the manner to facilitate review of qualities indicated.  Prepare Samples to match the Architect's sample.  Include the following:

##### Specification Section number and reference.

##### Generic description of the Sample.

##### Sample source.

##### Product name or name of the manufacturer.

##### Compliance with recognized standards.

##### Availability and delivery time.

#### Submit Samples for review of size, kind, color, pattern, and texture.  Submit Samples for a final check of these characteristics with other elements and a comparison of these characteristics between the final submittal and the actual component as delivered and installed.

##### Where variation in color, pattern, texture, or other characteristic is inherent in the material or product represented, submit at least (3) three multiple units that show approximate limits of the variations.

##### Refer to other Specification Sections for requirements for Samples that illustrate workmanship, fabrication techniques, details of assembly, connections, operation, and similar construction characteristics.

##### Refer to other Sections for Samples to be returned to the Contractor for incorporation in the Work.  Such Samples must be undamaged at time of use.  On the transmittal, indicate special requests regarding disposition of Sample submittals.

##### Samples not incorporated into the Work, or otherwise designated as the Owner's property, are the property of the Contractor and shall be removed from the site prior to Substantial Completion.

#### Preliminary Submittals:  Submit a full set of choices where Samples are submitted for selection of color, pattern, texture, or similar characteristics from a range of standard choices, unless otherwise noted in specification section..

##### a.	The Architect will review and return preliminary submittals with the Architects notation, indicating selection and other action.

#### Submittals:  Except for Samples illustrating assembly details, workmanship, fabrication techniques, connections, operation, and similar characteristics, submit (3) sets.  The Architect will return one set marked with the action taken.

#### Maintain sets of Samples, as returned, at the Project Site, for quality comparisons throughout the course of construction.

##### Unless noncompliance with Contract Document provisions is observed, the submittal may serve as the final submittal.

##### Sample sets may be used to obtain final acceptance of the construction associated with each set.

### Distribution of Samples:  Prepare and distribute additional sets to subcontractors, manufacturers, fabricators, suppliers, installers, and others as required for performance of the Work.  Show distribution on transmittal forms.

#### 1.	Field samples are full-size examples erected on-site to illustrate finishes, coatings, or finish materials and to establish the Project standard.

##### a.	Comply with submittal requirements to the fullest extent possible.  Process transmittal forms to provide a record of activity.

## 1.11	QUALITY ASSURANCE SUBMITTALS

### Submit quality-control submittals, including design data, certifications, manufacturer's instructions, manufacturer's field reports, and other quality-control submittals as required under other Sections of the Specifications.

### Certifications:  Where other Sections of the Specifications require certification that a product, material, or installation complies with specified requirements, submit a notarized certification from the manufacturer certifying compliance with specified requirements.

#### 1.	Signature:  Certification shall be signed by an officer of the manufacturer or other individual authorized to sign documents on behalf of the company.

### Inspection and Test Reports:  Requirements for submittal of inspection and test reports from independent testing agencies are specified in Division 1 Section "Quality Control."

NOTE:  Architect to edit the action language to meet the intent of the language examples listed.

## 1.12	ARCHITECT'S ACTION

### Except for submittals for the record or information, where action and return is required, the Architect will review each submittal, mark to indicate action taken, and return promptly.

#### 1.	Compliance with specified characteristics is the Contractor's responsibility.

### Action Stamp:  The Architect will stamp each submittal with a uniform, action stamp.  The Architect will mark the stamp appropriately to indicate the action taken, as follows:

#### Final Unrestricted Release:  When the Architect marks a submittal "Approved for fabrication," the Work covered by the submittal may proceed provided it complies with requirements of the Contract Documents.  Final payment depends on that compliance.

#### Final-But-Restricted Release:  When the Architect marks a submittal "Incorporate Notations," the Work covered by the submittal may proceed provided it complies with notations or corrections on the submittal and requirements of the Contract Documents.  Submit corrected copies for record.  Final payment depends on that compliance.

#### Returned for Resubmittal:  When the Architect marks a submittal "Rejected, or Revise and Resubmit," do not proceed with Work covered by the submittal, including purchasing, fabrication, delivery, or other activity.  Revise or prepare a new submittal according to the notations; resubmit without delay.  Repeat if necessary to obtain different action mark.

##### a.	Do not use, or allow others to use, submittals marked "Rejected, or Revise and Resubmit" at the Project Site or elsewhere where Work is in progress.

#### Other Action:  Where a submittal is for information or record purposes or special processing or other activity, the Architect will return the submittal marked "Action Not Required."

### Unsolicited Submittals:  The Architect will discard unsolicited submittals without action.

# PART 2 - PRODUCTS (Not Applicable)

# PART 3 - EXECUTION (Not Applicable)

END OF SECTION 01300