To print this document the show/hide symbol (¶) must be off – this will enable the document to indicate the correct number of total pages.

NOTE:  This Section 01310 "Construction Schedules ” includes requirements administrative and procedural requirements for preparation, submittal, and updating of the Contractor’s construction schedules and reporting progress of the Work.  It is appropriate for small single contract work.  Revise paragraphs carefully to reflect specific project requirements, or delete them if they do not apply.  USE THIS SECTION WHEN THE PROJECT TO BE ADMINISTRATED HAS A CONSTRUCTION COST ESTIMATE UNDER $5,000,000.  Use Section 01315 “CPM Schedules” when the project to be administrated has a construction cost estimate over $5,000,000”.  The Project Manager must decide if it is appropriate to use Section 01315 “CPM Schedules” for a specific project under  $5,000,000.

The header and footer for each page of the Project Manual shall match the format, font (Times New Roman), size (11 pt), font style (BOLD & CAPITALIZED) and line boarders, of the header and footer shown herein.. The header of each page shall contain the Section Number, the Section Title, and the page number & number of pages as shown herein. The footer shall contain the project number in the right hand side as shown herein, including the Table of Contents.  Division 0 and 1 contain a revision date in the left side of the footer This date is to remain as it is for Department informational purposes only and should not be altered by the Architect/Engineer.

DO NOT include Paragraphs or parts of Paragraphs in the project manual, which have no applicability to the specific project.  KEEP IN NUMERICAL SEQUENCE, If A PART IS NOT USED OR ELIMINATED THEN RENUMBER THE FOLLOWING SECTIONS.  IF A PART IS NOT APPLICABLE TO A SPECIFIC PROJECT THEN DESIGNATE IT AS (NOT APPLICABLE).  Also, please review the General Conditions carefully and coordinate the requirements of those Articles including the Definitions.

# PART 1 - GENERAL

## 1.1	RELATED DOCUMENTS

### A.	Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division 1 Specification Sections, apply to this Section.

## 1.2	SUMMARY

### A.	This Section includes administrative and procedural requirements for the preparation, submittal, and updating of the Contractor’s construction schedules and reporting progress of the Work.  It is appropriate for small single contract work.

#### 1.	Refer to the General Conditions and the Agreement for definitions and specific dates of Contract Time.

### B.	This Section includes the following:

#### 1.	Format.

#### 2.	Content.

#### 3.	Revisions to schedules.

#### 4.	Submittals.

#### 5.	Distribution.

### C.	Related Sections:  The following Sections contain requirements that relate to this Section:

#### Division 1 Section 01027 "Application for Payments" specifies requirements for submitting Schedule of Values and  Application for Payments.

#### Division 1 Section 01200 "Project Meetings" specifies requirements for submitting and distributing meeting and conference minutes.

#### Division 1 Section 01300 "Submittals" specifies requirements for submitting the the Submittal Schedule.

NOTE:  Select .either Section 01310 “Construction Schedule” or Section 01315 “CPM Schedule” as appropriate for project and delete the other Section.

#### Division 1 Section 01400 "Quality Control" specifies requirements for submitting inspection and test reports.

#### Division 1 Section 01600 "Materials and Equipment" specifies requirements for submitting the list of products.

## 1.3	DEFINITIONS

### A.	Construction Schedule: A method of planning and scheduling a construction project utilizing a horizontal bar chart with a separate bar for each major portion of the Work or operation to make the schedule an effective tool for planning and monitoring the progress of the work.

## 1.4	QUALITY ASSURANCE:

NOTE:  Retain paragraph below where the Work will be conducted under a single prime contract.  Delete for multiple prime contracts.  Revise if the owner wants to retain an independent consultant.

### A.	The Contractor's Consultant: Retain a consultant to provide planning, evaluating, and reporting by CPM scheduling.

NOTE:  Delete subparagraph below if bidders are not qualified construction scheduling operators or would not be acceptable as operators if qualified.  Delete if the Owner Representative wants contractor to retain an independent consultant.  Review these options with the Owner Representative.  Independent consultants should be impartial in the case of separate prime contractors or if small uncomplicated project.

#### 1.	In-House Option: The Owner may waive the requirement to retain a consultant if the Contractor can demonstrate that:

##### a.	The Contractor has the computer equipment required to produce construction schedules.

##### b.	The Contractor employs skilled personnel with experience in construction scheduling and reporting techniques.

NOTE: Insert a specific computer program and hardware configuration if the Microsoft Project program is unacceptable.

#### 2.	Program:  Use “Microsoft Project”, latest version.

NOTE:  Manual referenced in subparagraph below contains basic recommendations for construction scheduling procedures and methods.

#### 3.	Standards:  Comply with procedures contained in AGC's "Construction Planning & Scheduling."

## 1.5 	PRELIMINARY SCHEDULE

### A.	Preliminary gantt schedule is to be prepared by the General Contractor and submitted to the Construction Administrator within seven days of award of contract.  This schedule is to cover all items of Work from the start of the project up to the completion of the project.  This schedule must be revised when the actual schedule of significant items varies more than one week from the proposed schedule.

## 1.6	CONSTRUCTION SCHEDULE FORMAT

NOTE:  Retain paragraph below where the work will be conducted under a single prime contract.  Delete for multiple prime contracts.  Revise if the owner wants to retain an independent consultant.

#### 1.	Format:  Utilize a horizontal bar chart (gantt) with a separate bar for each major portion of the Work or operation, identifying first work day of each week.

NOTE: Insert a specific computer program and hardware configuration of and resource loaded Microsoft Project , latest version of the program.

#### 2.	Program:  Use Microsoft Project, latest version.

NOTE: Edit Sequence of listings in paragraph below as required for project.

#### 3.	Sequence of Listings:  Utilize the Table of Contents of this Project Manual and the chronological order of the start of each item of work.

#### 4.	Scale and Spacing: Provide space for notations and revisions.

NOTE: Edit sheet size  in paragraph below as required for project.

#### Sheet Size:  To be coordinated with Construction Administrator.

## 1.7	CONTENT

NOTE:  Edit and revise paragraphs below to suit project.

### Show complete sequence of construction by activity, with dates beginning and completion of each element of construction.

### Identify each item by specification section numbers.

### Identify work of separate phases other and other logically grouped activities.

### Show accumulated percentages of completion of each item, and total percentage of Work completed, as of the first day of each month.

### Provide separate schedule of submittal dates for shop drawings, product data, and samples, Owner/Agency furnished products and any products identified as under Allowances, and dates reviewed submittals will be required from Architect/Engineer.  Indicate decision dates for selection of finishes.

### Indicate delivery dates for Owner/Agency furnished products and any products identified as under Allowances.

### Indicate critical path with original baseline indicated.

### Coordinate content with Schedule of Values specified in Section 01027 “Application for Payments”.

## SUBMITTALS AND REVISIONS TO SCHEDULES

### An initial bar graph schedule is to be prepared by the General Contractor and submitted to the CA Refer to item 1.5.

### Indicate progress of each activity to date of submittal, and projected completion date of each activity.

### Identify activities modified since previous submittal, major changes in scope, other identifiable changes.

### Provide narrative report to define problem areas, anticipated delays, and impact on Schedule.  Report corrective action taken, or proposed, and its effect.

NOTE:  Projects requiring a Construction Schedule should begin with a preliminary bar-chart (gantt) schedule of the type described below.  Revise times given in paragraph below to suit project.

### Schedules must be revised monthly and when the actual schedule of significant items varies more than (7) calendar days from the proposed schedule.

### Submit revised Construction Schedules for each Application for Payment.

### Submit (4) four copies of the Construction Schedule to the Construction Administrator.

## 1.9	DISTRIBUTION

### Distribute copies of the Construction Schedules to Construction Administrator, Architect, Owner, Subcontractors, suppliers, and other concerned parties.

### Instruct recipients to promptly report, in writing, problem anticipated by projections indicated in schedules.

# PART 2 - PRODUCTS (Not Applicable)

# PART 3 - EXECUTION (Not Applicable)

END OF SECTION 01310