## PROCEDURE & INSTRUCTIONS
Construction Start Date and Notice to Proceed
State of Connecticut |  |  | Department of Public Works
Form 700 Construction Start Date and Notice to Proceed is used to notify the General Contractor (GC) and the Construction Administrator (CA) of the Official Construction Start Date. It is on this date that the number of days contractually allowed for the completion of the project, Substantial Completion, begins. This date is the day the clock starts ticking. This form is, also, the official record of that part of the proceedings of the meeting which established the Official Contract Start Date.
By receipt of this form, the GC acknowledges the notification and accepts the direction to proceed with the actual construction of the project commencing on the official Construction Start Date. The project is to be substantially complete and ready for occupancy, by the user agency, on or before the Date of Substantial Completion, unless that Date is extended by DPW authorized change order(s). A change order must be signed by the Project Manager to be authorized.
Copies of the signed, completed Form 700 are to be forwarded to the Construction Administrator, Consultant of Record and the Agency Representative. Copies are, also, to be forwarded to the Procurement, Communications and Process Management units.
This form, also, allows the user to make entries manually when electronic equipment is not available. This form is to be completed and dated on the same day as the meeting to establish the project Start Date.
Instructions: Enter data in the lightly bordered spaces only
1 | The Date will be entered electronically
2 | Insert General Contractor's business name and address
3 | Insert Project Manager's name, Team and Room Number
4 | Enter Project Number, Name and Location
5 | Enter the Project Contract Amount
6 | List all meeting attendees, firms or other entities, telephone and/or fax number. If
necessary, attach Continuation Page for additional attendees
7 | The Project Number will be inserted electronically
8 | Enter the agreed upon Contract Start Date
9 | Insert the number of Calendar days allowed for this project
10 | The Date of Substantial Completion will be computed electronically
11 | Enter the business name of the General Contractor and type or print the name of the person signing for the GC. Have signatory date the signature
12 | Insert Project Manager's name. Sign and date
13 | Enter the names and addresses of the CA, Consultant and Agency Representative
14 | Be sure to obtain signatures before making copies for distribution to the CA, Consultant and Agency Representative
15 | File the completed, signed form in the PROJECT FILE
16 | File other copies as indicated

## FORM 700
Construction Start Date and Notice to Proceed
State of Connecticut | [10 empty] | Department of Public Works
Date:
To: | [9 empty] | Project Number:
General Contractor
Address: | [8 empty] | Project Name
and Location:
From: |  | Project Manager: | [6 empty] | Team: |  | Room No.:
Contract Amount:
This is to record a meeting held on |  |  |  |  | 0 |  |  | which established the Official Construction Start Date
for commencement of work for the Department of Public Works Project Number: | [10 empty] | 0
Attending | [5 empty] | Entity |  |  |  |  | Telephone/Fax Number
Notification is hereby made that the Official Construction Start Date for Project Number: | [11 empty] | 0
is |  |  |  | and shall continue for |  |  |  |  | CONSECUTIVE CALENDAR DAYS, unless such time is
extended by authorized DPW Change Order(s). The Date of Substantial Completion shall be: | [12 empty] | 0 |  | .
The Construction Administrator will set the date and time for, and will notify all interested parties of, an on-site job meeting to be held prior to the Contract Start Date.
NOTE:
1 | The General Contractor is advised that the State of Connecticut will not grant an extension of time for late delivery of materials.
2 | The General Contractor is advised not to proceed with any change order work prior to receiving an official Change Order or an official Construction Change Directive signed by the Project Manager authorizing such work.
3 | The General Contractor acknowledges both the Construction Start Date and the Notice to Proceed and the receipt of a packet containing the following documents: CHRO placard; signed Order of Award; signed Executed Contract; Purchase Order. Also received is a Compact Disk with standard DPW forms for contractors' use. This CD includes an "Application and Certification for Payment," form for transcribing the Schedule of Values, as well as a drawing of the Project Sign for reproduction in plywood and erection at the site.
Received and Accepted by the General Contractor | [6 empty] | 0
by its Authorized Representative:
[8 empty] | signature | [5 empty] | date
Project Manager: |  |  | 0
[8 empty] | signature | [5 empty] | date
Provide Signed Copies for: | [5 empty] | Construction Administrator:
Address:
Consultant:
Address:
Agency Representative:
Address:
Copies for Department of Public Works: Procurement; Communications; Process Management
File: |  | Team | 0 |  | Process Management |  |  |  | File R3 | 0