## PROCEDURE & INSTRUCTIONS
Construction Change Directive Procedure
State of Connecticut |  |  |  | Department of Public Works
A Construction Change Directive (CCD), Form 737, is issued by the Project Manager to the General Contractor in those few instances when:
An agreement on the value of a Change Order Proposal cannot be reached
or
The Work encompassed by the Change Order cannot be specifically defined or delimited
or
An Emergency situation arises.
All work performed by the General Contractor or the General Contractor’s Subcontractors shall be performed on a Time and Material (Cost Plus) basis. A daily record of each day’s work must be maintained. This report must be completed and signed by the General Contractor, the General Contractor's Subcontractor(s), if any, and DPW’s representative (PM, APM or CA), on the day the work is done. At the conclusion of the work under the CCD, the General Contractor will prepare and submit, to the Project Manager, a Change Order Proposal (COP), Form 734, with all of the completed and signed daily reports attached for verification of the charges for materials, equipment and Labor. DPW Form 740 is available for this purpose but it is not mandatory that this particular form be used. Any other form that will supply the same information as Form 740 is permitted.
Instructions: |  |  | Enter data in lightly bordered blank areas only.
1 | Enter Potential Change Order No., Request For Information No., Proposal Request No., this Construction Change Directive No., and the Date..
2 | Address this form to the General Contractor, enter the Project Manager's name.
3 | Insert the Dpw Project Number, Project Name and Location.
4 | Enter the Change(s) to be made to the contract in the space provided.
5 | Enter the Not to Exceed amount of the of the proposed change(s) to the contract.
6 | The Project Manager shall sign and date this document and forward the original, signed and dated CCD to the General Contractor for signature and dating by its authorized representative with a copy for the GC's use. The CCD becomes effective immediately upon that date. The GC is obligated to return the signed original to the PM.
7 | When required, CSU authorized personnel shall review and sign the original CCD.
8 | Copies and file as required.

## FORM 736
Construction Change Directive
| State of Connecticut | [8 empty] | Department of Public Works
| PCO No. |  | RFI No. |  | PR No. | Construction Change Directive No.: |  |  | Date:
m/dd/yr
| To: | [5 empty] | Department of Public Works Project No.:
|  | General Contractor |  |  |  |  | Project Name
| From: | [5 empty] | and Location:
Project Manager
In accordance with the requirements of Article 13 of the General Conditions, the Contractor is hereby authorized and directed to make the following change(s), noted below, to the Contract. All work under this Construction Change Directive shall be done on a Time and Material (Cost Plus) or Unit Price basis:
The basis for the final amount of adjustment to the Contract Sum shall be follows:
The final amount shall be subject to a Change Order Proposal cost review and Change Order approval in accordance with the requirements of Article 13 of the General Conditions.
The amount of this Construction Change Directive for labor and materials shall not exceed:
When signed by the Project Manager and received by the Contractor, as evidenced by the dated signature of the Authorized Representative of the General Contractor, this document, as of this date, becomes EFFECTIVE IMMEDIATELY as a Construction Change Directive (CCD), and the Contractor shall proceed with the above noted change(s).
| Project Manager |  |  | 0
[8 empty] | signature |  | date:
Signature by the General Contractor or authorized representative indicates the Contractor’s agreement with the basis for the final amount of adjustment in the Contract Sum as set forth in this Construction Change Directive (CCD).
| General Contractor |  |  | 0
by:
|  |  | typed or printed name of Authorized Representative |  |  |  |  | signature |  | date:
CSU USE ONLY
Reviewed by
|  |  |  | typed or printed name |  |  |  | signature |  | date:
Reviewed by
|  |  |  | typed or printed name |  |  |  | signature |  | date:
Copies: GC (2 – Return signed original to DPW) | [8 empty] | File YH3 | 0