## PROCEDURE & INSTRUCTIONS
Cost Plus Work Contractor's Daily Report
State of Connecticut |  |  |  | Department of Public Works
Cost Plus Work, also referred to as Time and Material (T & M) or Labor and Material, is a method that may be used when the Owner and the General Contractor fail to agree on the cost of a change to the Work of the project. Form 740, Cost Plus Work Contractor's Daily Report, may be utilized to determine the actual charges for labor, materials, equipment, etc. used in effecting the change to the Work. By certifying the work done on a daily basis, an accurate charge for the total of work completed for the change to the Work of the project can be obtained.
The accuracy of the daily report depends on the diligence of the CA, whether DPW or contracted. By observing and noting the number of workers, the hours worked and the materials used, daily, the CA, the GC and any subcontractor(s) can all certify to the correctness of the Contractor's Daily Report
Upon completion of the change to the Work of the project, the daily reports are summarized by the GC and made a part of Change Order Proposal Workbook Form 735, attached to Change Order Proposal Form 734 and presented to the Project Manager.
Instructions |  |  | Enter data in the lightly bordered blanks only
1 | Insert either the Change Order Proposal (COP) Number or the Construction Change Directive(CCD) Number.
2 | Enter the Report Number and the Date.
3 | Enter the Project Number the Project Name and Location.
4 | Enter a complete, concise Description of the Cost Plus Work completed this day.
5 | Insert the Quantity, Unit of measurement and Description of Materials and/or Equipment Used This Day. If more space is necessary go to the CP MATERIAL tab to open the Cost Plus Work Daily Report Continuation Page Additional Material and/or Equipment.
6 | Enter the Labor Classification, the Number of Workers who worked on This Day and the Total Hours worked This Day per line item. For example: If 2 carpenters worked for 2 hours and one carpenter worked for 3 hours the Total Hours for the day would be 7 (2 x 2 + 3). If more space is necessary go to the CP LABOR tab to open the Cost Plus Work Daily Report Continuation Page Additional Labor Classification.
7 | Print the names of and obtain the signatures of the representatives of DPW, the GC and any subcontractor(s).
8 | The CA shall retain all original, signed copies for comparison with the forms attached to the GC's ultimate Change Order Proposal.

## FORM 740
Cost Plus Work Contractor's Daily Report
State of Connecticut | [9 empty] | Department of Public Works
THIS REPORT MUST BE COMPLETED AND SIGNED ON THE SAME DAY THAT THE WORK IS DONE
Attached to and forming part of COP Number: | [5 empty] | OR | CCD Number:
|  | Report Number: | [5 empty] | For work done on this Date:
Project Number: |  | BI-FKJ-987 |  |  | Project Name
and Location:
Description of the Cost Plus Work completed this day:
Quantity | Unit | Description of Materials and/or Equipment Used This Day
|  | When checked see attached |  |  | Continuation Page for Additional Material/Equipment
Labor Classification Per Dept. of Labor Wage and Workplace Standards Division | [7 empty] | Number of Workers This Day | Total Hours This Day
|  | When checked see attached |  |  | Continuation Page for Additional Labor Classification
CERTIFIED CORRECT
Department of Public Works |  |  | General Contractor |  |  |  | Subcontractor
by: |  |  | by: |  |  |  | by:
| printed name |  |  | printed name |  |  |  | printed name
| signature |  |  | signature |  |  |  | signature
Copies: | [7 empty] | FileYH3 |  | BI-FKJ-987

## CP MATERIAL
Cost Plus Work Daily Report Continuation Page Additional Material and/or Equipment
THIS REPORT MUST BE COMPLETED AND SIGNED ON THE SAME DAY THAT THE WORK IS DONE
Attached To and Forming Part of Contractor’s Daily Report of Cost Plus Work Number: | [10 empty] | 0
ctdpw
[6 empty] | For work done on this Date: |  |  |  | 0
Project Number: |  |  | BI-FKJ-987 |  |  | Project Name |  | 0
[6 empty] | and Location: |  | 0
0
Quantity |  | Unit | Description of additional Materials and/or Equipment Used this Day Only
CERTIFIED CORRECT
Department of Public Works |  |  |  | General Contractor |  |  |  | Subcontractor
by: | 0 |  |  | by: | 0 |  |  | by: | 0
| printed name |  |  |  | printed name |  |  |  | printed name
| signature |  |  |  | signature |  |  |  | signature
Copies: | [8 empty] | File YH3 |  | BI-FKJ-987
0

## CP LABOR
Cost Plus Work Daily Report Continuation Page Additional Material and/or Equipment
THIS REPORT MUST BE COMPLETED AND SIGNED ON THE SAME DAY THAT THE WORK IS DONE
Attached To and Forming Part of Contractor’s Daily Report of Cost Plus Work Number: | [10 empty] | 0
|  |  |  | For work done on this Date: | [5 empty] | 0
Project Number: |  | BI-FKJ-987 |  |  | Project Name |  | 0
[5 empty] | and Location: |  | 0
0
Labor Classification Per Department of Labor Wage and Workplace Standards Division | [9 empty] | Number of Workers This Day | Total Hours This Day
CERTIFIED CORRECT
Department of Public Works |  |  | General Contractor |  |  |  |  | Subcontractor
by: | 0 |  | by: | 0 |  |  | by: | by: | 0
| printed name |  |  | printed name |  |  |  | printed name
| signature |  |  | signature |  |  |  | signature
Copies: | [8 empty] | File YH3 |  | BI-FKJ-987
0